## Quick Wins
BrightIQ -- Quick Wins -- kittyessentials.co.uk
10 quick wins to action this week · Score: 76.6/100 (B) · Audited 15 June 20 · Sorted by impact · kittyessentials.
Priority | Action | Effort | Impact | Pages | Audience | Status | Notes
P1 | Add og:title, og:description, og:image, and og:url meta tags to every page | Medium | High | 48 | Content
P1 | Ensure all links have descriptive text visible to screen readers | Medium | High | 43 | Seo
P1 | Replace generic anchor text ('click here', 'read more') with descriptive phrases that tell users and search engines what the linked page is about (e.g., 'view our SEO audit services' instead of 'click here') | Medium | High | 43 | Seo
P1 | Choose either trailing slash (/page/) or no trailing slash (/page) and apply it consistently across your site | Medium | High | 33 | Dev
P1 | Add Article or BlogPosting schema to all blog posts and news articles | Medium | High | 32 | Dev
P1 | Add internal links from related pages to strengthen weak pages | Medium | High | 20 | Seo
P1 | Clean up sitemap 404s immediately — these waste crawl budget on every crawl cycle | Medium | High | 20 | Dev
P1 | Add a single, unique H1 tag to every page | Medium | High | 14 | Content
P2 | Add descriptive alt text to every image | Low | Medium | 9 | Content
P3 | Investigate slow pages for server-side bottlenecks, unoptimised database queries, large uncompressed assets, or missing CDN coverage | Low | Low | 4 | Dev

## Priority Actions
BrightIQ -- Priority Actions -- kittyessentials.co.uk
10 priority actions · Score: 76.6/100 (B) · Audited 15 June 20 · Sorted by severity and impact · kittyessentials.
Priority | Severity | Issue | Affected Pages | Impact | Fix | Audience | Effort | Status
P1 | ▌ Critical | Title tag present and appropriate length | 134 | Title tags are the first thing users see in Google search results. Poor titles reduce click-through rates, meaning less traffic from the same rankings. | Rewrite affected title tags to 50-60 characters. Include your primary keyword near the beginning. Make each title unique across the site. | Content | High
P1 | ▌ Critical | H1 tag present and unique | 14 | The H1 is the strongest on-page signal for search engines. Missing or duplicate H1s weaken topical relevance and can confuse crawlers. | Add a single, unique H1 tag to every page. The H1 should clearly describe the page topic and include your target keyword. | Content | Medium
P2 | ▌ Critical | Viewport meta tag present | 1 | Without a viewport meta tag, pages render incorrectly on mobile devices and may be penalised in mobile-first indexing. AI bots that render pages also need this tag for correct layout interpretation. | Add <meta name="viewport" content="width=device-width, initial-scale=1"> to the <head> of every page. This is essential for mobile usability and AI bot rendering. | Seo | Low
P3 | ▌ High | Cache headers configured | 200 | Proper caching reduces server load and improves repeat visit speed. Without any cache directives, browsers must re-download resources on every page view, increasing load time for returning visitors. | Configure Cache-Control headers on your server. For static sites, use Cache-Control: public, max-age=3600 (1 hour). For SPAs and dynamic sites, Cache-Control: no-cache (revalidate each visit) is acceptable. For static assets (CSS, JS, images), use max-age=31536000 (1 year) with content-hashed filenames. | Dev | High
P3 | ▌ High | Internal links pointing to redirects | 198 | Internal links to redirecting URLs force search engines to make extra requests, wasting crawl budget. Each hop also loses a small percentage of link equity, meaning less ranking power reaches the destination page. | Update internal links to point directly to the final destination URL. Each redirect hop wastes crawl budget and loses a small amount of link equity. Use search-and-replace or a redirect mapping to fix these in bulk. | Seo | High
P3 | ▌ High | DOM size within limits | 198 | Google recommends keeping DOM size under 1,500 elements. Excessive DOM nodes slow rendering, increase memory usage, and degrade Interaction to Next Paint (INP). Pages with 3,000+ elements can cause visible jank on mobile devices. | Reduce source DOM size to under 1,500 elements. Common causes: mega-menus with hundreds of links (consider lazy-loading the menu or using a flyout), CMS page builders (Elementor, Divi) that generate excessive wrapper divs, and unoptimised JavaScript frameworks. Note: WordPress themes with large mega-menus are a common cause — the fix may be a theme change, not content removal. Audit with Chrome DevTools Elements panel. | Dev | High
P3 | ▌ High | Duplicate JavaScript loaded | 198 | Duplicate JS doubles the download and parse cost for no benefit. jQuery loaded twice adds ~180KB of unnecessary transfers, directly impacting page speed scores. | Remove duplicate JavaScript libraries. Loading the same library twice wastes bandwidth, increases parse time, and can cause conflicts. This commonly happens on WordPress sites with multiple plugins that each bundle their own copy of jQuery. | Dev | High
P3 | ▌ High | Render-Blocking Resources | 198 | Render-blocking resources delay the first paint, increasing perceived load time. Reducing them can improve FCP by 1-3 seconds on typical sites. | Add 'async' or 'defer' to non-critical scripts, inline critical CSS, and use 'media' attributes on non-essential stylesheets to prevent render blocking. | Dev | High
P3 | ▌ High | Images use modern formats | 190 | Modern image formats reduce page weight by 25-50% per image (Google's own benchmark data). For image-heavy pages, this can save hundreds of KB, directly improving Core Web Vitals scores and page load speed. | Convert images to WebP or AVIF format for 25-50% smaller file sizes with equivalent quality (e.g., product-hero.jpg → product-hero.webp). Most CDNs and CMSes support automatic format conversion. Note: PNGs used for logos, icons, or images requiring transparency are exempt. | Content | High
P3 | ▌ High | Link equity flow analysis | 168 | Authority hoarders waste link equity by absorbing it without passing it on. Starved pages struggle to rank because they receive too little internal authority. | Add outbound links from authority-hoarding pages to distribute equity. Add more inbound links to starved pages from high-authority hub pages. | Seo | High

## Roadmap
BrightIQ -- Roadmap -- kittyessentials.co.uk
26 actions across 90-day plan · Score: 76.6/100 (B) · Audited 15 June 20 · Filter Timeframe = 0-30 days for this month · kittyessentials.
Timeframe | Priority | Action | Category | Effort | Status
0-30 days | P1 | Add a single, unique H1 tag to every page | Content | Medium
0-30 days | P2 | Add <meta name="viewport" content="width=device-width, initial-scale=1"> to the <head> of every page | Technical | Low
30-60 days | P1 | Rewrite affected title tags to 50-60 characters | Content | High
30-60 days | P2 | Ensure all links have descriptive text visible to screen readers | Technical | Medium
30-60 days | P3 | Replace generic anchor text ('click here', 'read more') with descriptive phrases that tell users and search engines what the linked page is about (e.g., 'view our SEO audit services' instead of 'click here') | Architecture | Medium
30-60 days | P3 | Choose either trailing slash (/page/) or no trailing slash (/page) and apply it consistently across your site | Architecture | Medium
30-60 days | P3 | Add Article or BlogPosting schema to all blog posts and news articles | Technical | Medium
30-60 days | P3 | Add internal links from related pages to strengthen weak pages | Architecture | Medium
30-60 days | P3 | Clean up sitemap 404s immediately — these waste crawl budget on every crawl cycle | Architecture | Medium
30-60 days | P3 | Add descriptive alt text to every image | Technical | Low
30-60 days | P3 | Investigate slow pages for server-side bottlenecks, unoptimised database queries, large uncompressed assets, or missing CDN coverage | Technical | Low
30-60 days | P3 | Remove rel='nofollow' from internal links | Architecture | Low
30-60 days | P3 | Add a self-referencing canonical tag to every page | Content | Low
30-60 days | P3 | Improve Core Web Vitals by optimising images (WebP, lazy loading), minimising render-blocking resources, and reducing server response time. | Technical | Low
60-90 days | P1 | Configure Cache-Control headers on your server | Technical | High
60-90 days | P2 | Update internal links to point directly to the final destination URL | Architecture | High
60-90 days | P3 | Reduce source DOM size to under 1,500 elements | Technical | High
60-90 days | P3 | Remove duplicate JavaScript libraries | Technical | High
60-90 days | P3 | Add 'async' or 'defer' to non-critical scripts, inline critical CSS, and use 'media' attributes on non-essential stylesheets to prevent render blocking. | Technical | High
60-90 days | P3 | Convert images to WebP or AVIF format for 25-50% smaller file sizes with equivalent quality (e.g., product-hero.jpg → product-hero.webp) | Technical | High
60-90 days | P3 | Add outbound links from authority-hoarding pages to distribute equity | Architecture | High
60-90 days | P3 | Add internal links pointing to orphan pages from relevant content or navigation | Architecture | High
60-90 days | P3 | Add explicit width and height attributes to all <img> tags, matching the image's actual dimensions (e.g., <img width="800" height="600">) | Technical | High
60-90 days | P3 | Add Product schema (JSON-LD) to all product pages with: name, description, image, price (via Offer), availability, brand, and aggregateRating if reviews exist | Technical | High
60-90 days | P3 | For internal HTTP links, update URLs to HTTPS — this indicates incomplete HTTPS migration and is always fixable | Architecture | High
60-90 days | P3 | Write unique meta descriptions of 120-155 characters for each page | Content | High

## AI Visibility
BrightIQ -- AI Visibility -- kittyessentials.co.uk
Moderate AI readiness: 4/6 AI Readiness checks passed (67%). Several gaps reduce visibility in AI search results.
Priority | Opportunity | Effort | Status | Notes
P2 | Add Organization schema to your homepage with: name, url, logo, description, and sameAs links to your social profiles (LinkedIn, Facebook, Twitter/X, Google Business Profile) | Medium
P2 | Create a /llms.txt file following the llmstxt.org specification | Medium